## Slide 1
Robotics at the YMCA
An eight-session MechaRAMS proposal for grades 7 and 8
Fall 2026 · Planning draft
Notes: Audience: YMCA partners and team leadership. Purpose: decide whether to launch a small pilot with existing equipment. Enrollment, devices, dates, and staffing are unconfirmed. Source: user-provided partnership context. No claim of past outcomes.

## Slide 2
The proposed pilot
8 students in four pairs
2 existing SPIKE Prime kits
8 weekly meetings of 60 minutes
2 trained student mentors minimum, plus an adult lead
Notes: All quantities except the two user-reported kits are recommendations. Four laptops are preferred, two are workable with paper planning tasks. Four mentors are ideal, but one prepared mentor per kit pod is the minimum instructional recommendation. YMCA staffing requirements still govern.

## Slide 3
A new mission each week
Weeks 1–2 Signals, movement, and a measured delivery
Weeks 3–4 Repeating routines and sensor decisions
Weeks 5–6 Floor markers and a student-built attachment
Weeks 7–8 A community mission and family showcase
Notes: The same base stays assembled. This preserves programming and testing time. Every pair gets about 17 minutes of direct kit time in the standard lesson, plus planning and discussion. Full details are in the program proposal and instructor guide.

## Slide 4
Python students can reason about
travel = 180
await drive(travel)
await signal("D")
Predict. Change one value. Run. Explain the result.
Notes: These are real Python recipe lines inside supplied support code. They are not draggable Python blocks. Mentors introduce only the relevant lines, then expose loops and sensor conditions over time. Word Blocks is a planned fallback with the same learning goal. Source for supported languages and app entry point: https://education.lego.com/en-us/downloads/spike-app/software/

## Slide 5
The decisions before registration
Confirm enrollment, devices, and eight meeting dates.
Inspect both kits and rehearse every mission.
Confirm supervision, pickup, storage, and charging.
Agree how the YMCA and team will evaluate the pilot.
Notes: Illustrative schedule: October 21 and 28; November 4, 11, and 18; December 2, 9, and 16, 2026. Skip Thanksgiving week. Check November 11 and local closures. The kit software and lesson support continue to June 30, 2031 despite SPIKE sales retirement. Source: https://education.lego.com/en-us/spike-update-2026/

## Slide 6
Learning and community benefit
Each student explains a program decision.
Each pair improves a design using test evidence.
High school mentors practice teaching and leadership.
The YMCA helps decide whether the program should repeat.
Notes: Use attendance, matched concept checks, work samples, and partner feedback. Future FRC interest and actual later participation are separate outcomes. Engineering Inspiration considers measurable community STEM work. Impact considers sustained work over time. This proposed pilot is one contribution, not evidence of outcomes already achieved. Sources: https://www.firstinspires.org/resources/library/frc/team-awards and https://www.firstinspires.org/resources/library/frc/submitted-awards